## Raid-Adventure-Test-Plan
G00346830 | Project Name: | Raid Adventure | Game Designed By: | NIKIJS PAULS | CUSTOMER
| Module Name: | Mobile Applications D3 | Game Design Recieved: | 2019-10-03
| Release Version: | Unity 2019.2.15f1 | Game Developed By: | ANDREAS FAHEY | DEVELOPER
| Game Dimension: | 2D | Game Tested: | 2019-12-12
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
00-1 | Start Game | Test Game Start Up, Check For Errors etc. | 1. Open Unity 2. Make Sure Your at Start Screen Scene 3. Press Play Button | Full Game | Game Should Start | Game Started | Pass | No Point continuing if this test failed
00-2 | Menu Functionality | Test for Menu Audio Press Play, Should bring you to Game Scene. | 1. Press Play Button. 2. Make sure volume is up for Audio. 3. Press "Play Game" on menu Screen. | Menu | Audio Should be Playing and when you press "Play Game" button should bring you to game scene. | Audio Playing & "Play Game" button brings you into game. | Pass | Audio Playing nicely on a loop so it dosen't turn off. Play Button works fine, brings you into game. Exit Button does not work in unity, not tested.
00-3 | Move Character | Move Character around scene. | 1. Ensure your in the game. 2. Use WASD or Arrorws on keyboard to move player around. | Player/Warrior | Player should move should move around freely using the keys. | Warrior moves freely around scene. | Pass | Implemented nicely.
00-4 | Warrior Collisions | Player should be able to collide with objects, and not get stuck. | 1. Ensure You're in the game. 2. Using the WASD or Arrow keys walk into objects. | Collisions | Player should be able collide with objects and enemy AI. | Warrior Collides with collide objects within created scene. | Pass | Sometimes there are bugs that I cant fix where warrior does get stuck but rare.
00-5 | Enemy AI Follow & Stop | Enemy AI should follow warrior/player on approach. When moving away from enemy, within distance enemy ai should stop following player. | 1. Ensure You're in the game. 2. Move Towards Enemy and get within radius of them to follow. 3. Walk Away from enemy until enemy stops following. Must be certain distance away from AI to stop following. | Enemy AI | Enemy should follow the player when player gets within distance of enemy. Enemy should stop following when player gets enough distance away. | Enemy Ai Follows & stops when player approaches and walks away respectively | Pass | Also wanted to note Enemy AI does get blocked by objects with collisions. It can be buggy though.
00-6 | Warrior Attack Button | Press Space Bar to attack with sword each direction, also sword audio should work. | 1. Ensure You're in the game. 2. Press space bar to swing sword for attack. | Player/Warrior | Player should swing sword when space key is pressed, also audio should work with swing. | Audio and Space bar entry works for sword. Pretty cool. | Pass | Nice addition of audio to game. Agreed on keyboard changes with customer.
00-7 | Warrior Attack Enemy AI | Should be able attack & kill enemy AI with sword. | 1. Ensure You're in the game. 2. Press space bar to swing sword for attack. 3. Go close enough for hitbox and attack enemy AI. Healths may vary for different enemies. | Player/Warrior/Enemy AI | Sword swing should strike enemies and take health away from them. Once gets to 0 health enemy dissapears | Enemies can be killed with 1 or more sword strikes depending on enemy | Pass | Knockback dosen't work for player but works for enemy ai, will be described in next test case.
00-8 | Enemy AI Attack Warrior | Enemy AI Should be able attack Player/Warrior & Taking Health away. | 1. Ensure You're in the game. 2. Walk towards enemy for them to detect player. 3. Allow Enemy to attack. | Player/Warrior/Enemy AI | While knocking back player enemy should be taking health of player in process | Enemy Knocks player/warrior back when touch/attack but no health added to player. | Fail | Tried copying enemy AI health to player script but abit more complex and didn’t want to break code. Knockback works however and can be adjust with thrust element in unity.
00-9 | Pause Menu | Check Functionality of pause menu. | N/A Pause Menu Not Implemented. | Pause | Be Able Pause Game in game scene. | N/A | Null | Didn't implement pause menu. Better time management needed.
00-10 | Exit Game | Exits Game while in main menu | 1. Press Play Button in Unity. 2. Press Exit Button. | Menu | Closes Game | N/A | Fail/Null | This dosen't function in unity code and button is there.
00-11 | Game Volume | Adjusts Volume of Game | N/A Not Implemented | Menu/Pause | Be Able Adjust Volume of gameplay and menu audio. | N/A | Null | Didn't implement volume adjust. Better time management needed.
00-12 | How To Win | Test Win | 1. Kill All Enemies in Game. 2. Complete levels. | Game Objective | Victory Should be displayed on screen and option to return to main menu. | Nothing Implemented for this. Game stops by manual unity stop. | Fail | Couldn't implement this. Wanted to add levels game getting harder each level. Better time management needed.